## Excel Guide
Case Study Guide / The Case Study on Program Increment Planning from Product Owner perspective contains a total of 2 documents: Document 1 (Planning Setup) provides the general information on team situation and planning context. Document 2 (Backlog Planning Details) provides the Product Backlog & capacity for the team. / This excel (Document 2, Backlog Planning Details) contains the Team Product Backlog and Team Capacity Calculation tabs. / Please do make use of the tabs to prepare your final presentation (in Power-Point format).

## Team Capacity Calculation
Team Product Page Capacity Planning			Team Capacity Exercise: / Determine the capacity of your team by a) defintion of relevant team members and b) definition of points per team members. / Feel free to make use of this calculation layout.
PI Capacity (in Points)
Testing Capacity (in Points)

Sprint 1
Start	7/11/2022
End	7/24/2022		Team Product Page Capacity Planning
Points	0		PI Capacity (in points)	189

Team member	Days off (Points reduction)	Points
			Sprint 1
			Start	7/11/2022
			End	7/24/2022
			Points	36

Sprint 2			Team member	Days off (Points reduction)	Points	Non-reduction
Start	7/25/2022		Maria	0	8	8
End	8/7/2022		Tim	0	8	8
Points	0		Ilya	0	8	8
			Wen	0	4	4
Team member	Days off (Points reduction)	Points	Me	0	8	8
			Sprint 2
			Start	7/25/2022
			End	8/7/2022
			Points	32

Sprint 3			Team member	Days off (Points reduction)	Points
Start	8/8/2022		Maria	2	6	8
End	8/21/2022		Tim	2	6	8
Points	0		Ilya	0	8	8
			Wen	0	4	4
Team member	Days off (Points reduction)	Points	Me	0	8	8
			Sprint 3
			Start	8/8/2022
			End	8/21/2022
			Points	31

Sprint 4			Team member	Days off (Points reduction)	Points
Start	8/22/2022		Maria	5	3	8
End	9/4/2022		Tim	0	8	8
Points	0		Ilya	0	8	8
			Wen	0	4	4
Team member	Days off (Points reduction)	Points	Me	0	8	8
			Sprint 4
			Start	8/22/2022
			End	9/4/2022
			Points	29

Sprint 5			Team member	Days off (Points reduction)	Points
Start	9/5/2022		Maria	0	8	8
End	9/18/2022		Tim	5	3	8
Points	0		Ilya	0	8	8
			Wen	2	2	4
Team member	Days off (Points reduction)	Points	Me	0	8	8
			Sprint 5
			Start	9/5/2022
			End	9/18/2022
			Points	25

Sprint 6			Team member	Days off (Points reduction)	Points		// Maria Himmelfahrt
Start	9/19/2022		Maria	1	7	8
End	10/2/2022		Tim	1	7	8
Points	0		Ilya	6	2	8
			Wen	2	2	4
Team member	Days off (Points reduction)	Points	Me	1	7	8
			Sprint 6
			Start	9/19/2022
			End	10/2/2022
			Points	36

			Team member	Days off (Points reduction)	Points
			Maria	0	8	8
			Tim	0	8	8
			Ilya	0	8	8
			Wen	0	4	4
			Me	0	8	8

## Product Backlog
Team Product Page Backlog					Ranking	High	Sprints	PI2 - Sprint 1
Total Capacity		Testing Capacity		per Sprint					Medium		PI2 - Sprint 2
189		0 (because Test-Driven Development)		31.5					Low		PI2 - Sprint 3
Product Backlog Exercise / Given the input of the Program Increment sessions on product vision, priorities and current program situation please do the following: / A) Assign a broader priority group to all features in the list (select between given categories low, medium, high) / B) Rank individual features (order the features from 1 - 19 according to importance for Program Increment target reach) / C) Define and list dependencies as they occur between different features [if applicable] / D) Define and list risks as they could be identified for features [if applicable] / E) Assign features to a sprint according to given capacity: Features have been estimated for you, they can be distributed across 2 sprints in a row.					PI2 - Sprint 4
				PI2 - Sprint 5
				PI2 - Sprint 6

Feature ID	Feature (Short Description)	Description	Acceptance Criteria	Priority	Rank	Size	Dependency	Risk	Sprint assigned
SFEAT00124	Product Title Display	As a customer, I want to see a unique identifiable product title, so that I can intuitively identify the product across the website.	1. Display the title at the top of the website next to the picture on the right side.	High	7	3	Testing Accuracy Increase		PI2 - Sprint 2
SFEAT00114	Product Page Picture and Alternate Views Display	As a customer, I need to have as many visual information as possible, so that I can get a good overview of the various parts of the product.	1. The main picture shall be displayed on the top left of the product page. / 1.2. Customer shall be able to zoom into main picture displayed. / 1.3. Main picture shall be changing according to selection from entire list. / 2. Additional product picture shall be displayed at 75% size reduction centered and beneath the main picture. / 3. 3 detailed pictures shall be displayed at the same time before scrolling through the list of pictures. / 4. List of pictures shall entail at least the following kinds: Product (alone), Product (in usage)	High	3	8	Testing Accuracy Increase	Subpar Implementation might cause Loading Time Problems because of high-res images / Mitigation: Page Speed Increase Feature at the end, so that flaws in all features can be found	PI2 - Sprint 1
SFEAT00125	Pricing information	As a customer, I want to have an overview of the product's price and possible discount options, so that I can get full transparency on costs.	1. Display the product price beneath the reviews summary / 2. Adjust the price based on sales & quantity regulations / 3. Inform the customer via a pop-up message on the availability of discounts or promotional offers. / 4. Reduced prices shall be displayed next to the reguar price which gets crossed	High	2	6	Testing Accuracy Increase		PI2 - Sprint 1
SFEAT00112	Testing Accuracy Increase	As a webshop provider, I need to ensure that my features are deployed correctly, so that my customers do have a high quality user experience.	1. Identification of tests which can be automated / 2. Automation of highly repetitive testing tasks	High	1	14		Developers need to be familiar with TDD, otherwise improper test cases might be written	PI2 - Sprint 1
SFEAT00111	Webshop - Page Speed Increase	As an online customer, I need to have a responsive website, so that I do not bounce from the website.	1. Load the website in maximum 3 seconds / 2. Ensure high picture resolution quality / 3. Reduce Java Script Usage whereever possible (spike task)	High	5	12	Everything		PI2 - Sprint 5	PI2 - Sprint 6
SFEAT00127	Product Quantity	As a customer, I want to be able to change the quantity to purchase, so that I can directly buy the correct number of products I require.	1. Display the purchase quantity below the product price / 2. Customers should not be able to purchase more than stock is available / 3. Display an out of stock message in case products are not available / 4. Display a notification on earliest shipment for which information is available	Low	14	6	Testing Accuracy Increase		PI2 - Sprint 2
SFEAT00122	Add to cart function	As a customer, I want to have the possibility to add items to my shopping cart, so that I can continue shopping for other items and return to payment at a later point in time.	a) Display button / 1. Display below Product Variables / 2. Display bigger in size than Product Variables / 3. Display next to product image / b) Place item in cart / 1. adjust cart value / 2. calculate based on size/amount	High	6	10	Testing Accuracy Increase / Pricing Information		PI2 - Sprint 2
SFEAT00116	Product Description Display	As a customer, I want to have an informative product description, so that I can get a good overview of the product characteristics.	1. Display the product description as a related tab beneath the basic production information and general interaction section / 2. Display all relevant product and brand information available	Medium	4	4	Testing Accuracy Increase		PI2 - Sprint 2
SFEAT00126	Product Star Review / Ranking	As a customer, I want to give a star ranking for a product, so that I can feedback and share my experience.	1. Display the Product Review beneath the product title. / A. Display the overall average rating in te format of stars as X/5 / B. Display the number of ratings made / 2. Allow guest accounts to view the ranking / 3. Allow logged-in users to rank products	Low	15	8	Testing Accuracy Increase		PI2 - Sprint 5
SFEAT00117	Consumer reviews on product	As a customer, I want to have an overview of past reviews, so that I can get information about the quality and user experience of former buyers.	1. Display the product reviews as a related tab beneath the basic production information and general interaction section / 2. Display reviews in chronological order starting with the most recent ones / 3. Customers can filter reviews according to ranking given	Low	16	12	Testing Accuracy Increase / Star Review		PI2 - Sprint 5
SFEAT00128	Trust Signals	As a customer, I want to see trusted signs along the purchasing process, so that I am reassured to be operating on a trustworthy website	1. Display the signals below the "add to cart" button	Medium	9	3	Testing Accuracy Increase		PI2 - Sprint 3
SFEAT00121	Product Variables Overview	As a webshop, I want to provide the customer with different product varieties, so that the customer can take a look at the entire product range.	1. Display coloring options / 2. Display sizing options	High	8	6	Testing Accuracy Increase		PI2 - Sprint 1
SFEAT00115	Product Page View Different colors	As a customer, I want to change colors of my product displayed, so that I can compare them with each other.	1. The pictures displayed on the product page shall be displayed according to the color being selected. / 2. Available colors shall be taken from the product variables section.	Medium	12	7	Testing Accuracy Increase / Product Page Picture and Alternate Views Display / Product Variables Overview	Subpar Implementation might cause Loading Time Problems because of high-res images / Mitigation: Page Speed Increase Feature at the end, so that flaws in all features can be found	PI2 - Sprint 4
SFEAT00129	Social Share Buttons	As a customer, I want to have the possbility to share products with my community, so that I can engage with others about the products I am interested in.	1. Display the buttons below the "add to wishlist" button / 2. Add instagram, facebook, pinterest, tiktok, snapchat	Medium	10	22	Testing Accuracy Increase	Effort to implement Social Share Buttons is probably heavily overestimated	PI2 - Sprint 3
SFEAT00119	Add to wishlist function	As a customer, I want to have the possibility to add items to my wishlist, so that I can save my favourite items for a later point in time.	1. Display the wishlist button beneath the purchasing process	Low	17	6	Testing Accuracy Increase		PI2 - Sprint 4
SFEAT00120	Add to comparison function	As a customer, I want to have the possibility to compare items with each other, so that I can make an informed decision about different product options.	1. Display the comparison button next to the watchlist button on the right side	Low	13	8	Testing Accuracy Increase / Pricing Information		PI2 - Sprint 4
SFEAT00118	Related products	As a customer, I want to be informed about related products, so that I can be holistically informed about product usage.	1. Display related products at the bottom of the page / 2. Show items ranked by customer reviews starting with highly ranked products first / 3. Show items first being bought by other customers in the past.	Medium	11	6	Testing Accuracy Increase	Algorithm (delayed for 2 sprints) might be delayed more / Mitigation: Sprint 4 so that the other team has 1 Sprint as buffer	PI2 - Sprint 4
SFEAT00113	Enable English language	As an online customer, I need to have an English version of the pages, so that I can find all relevant information in an internationally known language.		High	7	5	Testing Accuracy Increase		PI2 - Sprint 2	PI2 – Sprint 6
SFEAT00123	Live-Chat	As a customer, I want to have the possibility to chat with a bot, so that I can get immediate answers to initial questions or be better directed to a customer service representative.	1. Display the chat-bot at the bottom right corner of the page / 2. Chat-Bot icon display after 10 seconds are spent by the user on the page / 3. Create a welcome message for the initial contact with customer saying "Got any questions? I am happy to help" / 4. Set different bot actions which include FAQ website and book a customer service appointment.	Low	18	27	Testing Accuracy Increase	Full-Capacity Sprints at the end / => Feature may not be finished in time / Mitigation: Live-Chat Feature can be released after the Webshop Launch, so no time pressure	PI2 - Sprint 6